## Project Timeline
FSAE SOFTWARE TIMELINE
PROJECT TITLE |  | FSAE Software |  | TEAM NAME | [6 empty] | FSAE
PROJECT MANAGER |  | Aidan Mcdougald |  | DATE | [6 empty] | 2024-09-25
PHASE |  |  | DETAILS | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  |  |  | DATE 2: SEP; DATE 7: OCT; 2024-09-25 11: NOV; 2024-09-25 15: DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY
| PROJECT SPLIT: |  |  | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
1 | Documents |  | - Software Development Plan Document [Complete] | SEP 23: Software Development Plan Document [Complete]; DEC 9: CODE FREEZE
|  |  | - Written Status Reports | SEP 30: Written Status Report; OCT 14: Written Status Report; OCT 28: Written Status Report; NOV 11: Written Status Report; NOV 25: Written Status Report
|  |  | - Oral Status Reports | OCT 7: Oral Status Report; OCT 14: Oral Status Report; OCT 21: Oral Status Report; OCT 28: Oral Status Report; NOV 4: Oral Status Report; NOV 11: Oral Status Report; NOV 18: Oral Status Report; NOV 25: Oral Status Report; DEC 2: Oral Status Report
|  |  | - Software Design Description Document [Archiecture Section] | OCT 21: Software Design Description Document [Archiecture Section]
|  |  | - Software Design Description Document [Detailed Section | NOV 4: Software Design Description Document [Detailed Section]
|  |  | - User Manual Final Updates | NOV 4: User Manual Final Updates
|  |  | - ALPHA/BETA/Critical Design Review Presentation/Demonstration | NOV 11: ALPHA/BETA/Critical Design Review Presentation/Demonstration
|  |  | - Final Documentation Updates | NOV 11: Final Documentation Updates
|  |  | - Final Project Presentation | NOV 25: Final Project Presentation
|  |  | - Final Report | NOV 25: Final Report
| Software |  | - Database CSC | OCT 7: Database CSC
|  |  | - Input Observer CSC | OCT 7: Input Observer CSC
|  |  | - Telemetry GUI CSC | OCT 21: Telemetry GUI CSC
|  |  | - Traction Control CSC | OCT 21: Traction Control CSC
|  |  | - Virtual Differential CSC | OCT 21: Virtual Differential CSC
|  |  | - Suspension Motor Controller CSC | NOV 4: Suspension Motor Controller CSC
|  |  | - Steering Wheel Unit Processor CSC | NOV 11: Steering Wheel Unit Processor CSC
|  |  | - Safety Check CSC | NOV 11: Safety Check CSC
|  |  | - Power Draw Monitor CSC | NOV 18: Power Draw Monitor CSC
|  |  | - Graphics Interface CSC | NOV 18: Graphics Interface CSC
|  |  | - Data Management CSC | NOV 25: Data Management CSC
|  |  | - Suspension Kinematics CSC | NOV 25: Suspension Kinematics CSC
|  |  | - Cheating Mode CSC | NOV 25: Cheating Mode CSC